## Timeline
CST8333 Ticket System Development TIMELINE
TIMELINE TEMPLATES by Vertex42.com
https://www.vertex42.com/ExcelTemplates/timeline.html
Tips for Using this Template
• Insert and delete entire rows when editing the data tables
• Avoid leaving the label column blank
• Format the horizontal axis to set min/max bounds
• Enter a vertical position between -100 and 50
• Format individual data labels or markers to highlight specific events
• Read cell comments in the table header row for more information
Other Notes
• Milestone leader lines are Y Error bars
• Task leader lines are Y Error bars
• Task durations are X Error bars
2024-06-06
Tasks
| Start | End | Duration | Label | Vert. Position | Vert. Line
| 2024-03-01 | 2024-03-09 | 8 | Decide Project | -25 | -25
| 2024-03-09 | 2024-03-17 | 8 | Define Purpose, Scope, Requirements | -50 | -25
| 2024-03-09 | 2024-05-26 | 57 | Iterate and Review Sprint Backlogs | -60 | -35
| 2024-03-17 | 2024-03-25 | 8 | Select Solution Type and Language | -75 | -25
| 2024-03-25 | 2024-03-31 | 7 | Draft Conceptual Design | -100 | -50
| 2024-03-31 | 2024-05-05 | 35 | Complete Working Prototype | -25 | -25
| 2024-03-31 | 2024-05-05 | 35 | Refine Requirements | -50 | -50
| 2024-05-05 | 2024-05-26 | 21 | Complete V1 of Product | -25 | 25
| 2024-05-26 | 2024-06-02 | 8 | Complete Testing | -50 | -50
Insert new rows above this one
Milestones
| Date |  |  | Label | Position
| 2024-03-01 |  |  | Start, Mar 1 | 30
| 2024-04-04 |  |  | Assignment 1: Due 04-Apr | 25
| 2024-05-09 |  |  | Assignment 2: Due 09-May | 20
| 2024-06-06 |  |  | Assignment 3: Due 06-Jun | 15
Insert new rows above this one
Formulas:
End = [Start]+[Duration]
End = [Start]+[Duration]-1
Start = [End, row above]
Start = [Start, row above]

## Sheet1
Requ’t Number | Requ’t Name | Category | Test Criteria | Expected Result | Result | Pass/Fail | Notes
TR-01 | Relational Database | Technology | Connect to the Database | Database connects successfully | N/A | N/A | N/A
TR-02 | Login Page GUI | Technology | User Can view Login UI | Page loads and user can login | N/A | N/A | N/A
TR-03 | Criteria Checkbox | Technology | Check off different checkboxes for different results | A password with all fitting criteria is created | N/A | N/A | N/A
TR-04 | Mysql Libraries | Technology | Import MySQL Libraries to IDE | Mysql Libraries Imported Successfully | N/A | N/A | N/A
TR-05 | Python Flask | Technology | Install and run python flask | Python Flask works and displays hello world | N/A | N/A | N/A
TR-06 | User login | Technology | Have a test username and password for attempting login testing | User is able to log in and begin password creation | N/A | N/A | N/A
TR-07 | Ticketing System UI | Technology | Have user attempt to access ticketing system | Users can view Ticking system UI, displaying all tickets | N/A | N/A | N/A
TR-08 | View Single Ticket UI | Technology | Have user attempt to view a single ticket | User is able to click on ticket number and view single view of tickmet | N/A | N/A | N/A
TR-09 | Create Ticket UI | Technology | User attempts to create a new ticket | New Ticket is created and added to ticketing system database | N/A | N/A | N/A
BR-01 | Password recovery | Business | Press "forgot password" link on login page | User is presented with security question, once answered user can update password | N/A | N/A | N/A
BR-02 | Case Management | Business | Access Ticketing System and verify it provides means to manage workflow | Ticketing system provides a list of cases that are active | N/A | N/A | N/A
BR-03 | Case Age | Business | Access Ticketing System and verify if cases have an age metric | Ticketing system shows list of cases and their age | N/A | N/A | N/A
BR-04 | User level based access | Business | Attempt to login via login page | When user is logged in they are given a different view depending on if they are a customer or an agent | N/A | N/A | N/A
BR-05 | Reporting | Business | Access ticket system export feature | System allows an agent to pull an export of all cases for reporting purposes | N/A | N/A | N/A
UR-01 | User Feedback | User | Survey User Feedback via Website | Users report satisfaction with product | N/A | N/A | N/A
UR-02 | Instructions | User | Users are given a instruction document and proceed to use application | Instructions are clear and allow user to fully operate application | N/A | N/A | N/A
UR-03 | Multiple Users | User | Users login and use application | Users are given a view based on their role | N/A | N/A | N/A
UR-04 | Tickets Associated to Customer | User | Customer creates a ticket for agent review | Ticket is created and has uneditable field of who ticket was created by and for | N/A | N/A | N/A
UR-05 | Guest login | User | Log in without credentials | User is allowed to create passwords | N/A | N/A | N/A
NF-01 | Web app works in multiple browsers | Non-Functional | Access Web UI in Chrome, Edge, Brave | Works in Multiple browsers | N/A | N/A | N/A

## About
PROJECT TIMELINE by Vertex42.com
https://www.vertex42.com/ExcelTemplates/project-timeline.html
About This Template
This template uses a scatter chart with data labels and error bars to create a project timeline that shows both milestones and tasks with durations. Unlike a Gantt chart, which shows each task on a separate row, you control the vertical positioning of tasks within the timeline. You can specify the length of the vertical leader line to help show task dependencies.
This type of project timeline is mainly useful for a general overview of a project rather than showing a detailed work breakdown structure.
More Templates
Visit Vertex42.com to download other timeline and project management templates.
More Timeline Templates
More Project Management Templates
About Vertex42
Vertex42.com provides professionally designed spreadsheet templates for business, home, and education - most of which are free to download. Their collection includes a variety of calendars, planners, and schedules as well as personal finance spreadsheets for budgeting, debt reduction, and loan amortization.
Businesses will find invoices, time sheets, inventory trackers, financial statements, and project planning templates. Teachers and students will find resources such as class schedules, grade books, and attendance sheets. Organize your family life with meal planners, checklists, and exercise logs. Each template is thoroughly researched, refined, and improved over time through feedback from thousands of users.